## Overview
Mirage CA Baseline v2026 — Tenant Deploy Runbook
Public reference implementation. Conditional Access policy baseline for Microsoft Entra ID. Companion to the 'CA Baseline' and 'CA Baseline Summary' workbooks (per-policy specifications).
Section | Description
About | A 40-policy Conditional Access baseline for SMB / mid-market M365 tenants. Organized around 6 personas: All users, Admins, Application, Service, Guest, Agent. Each policy is identified by a CAxxx code (CA1xx = all-users, CA2xx = mobile, CA3xx = device compliance, CA6xx = admins, CA7xx = per-app, CA8xx = service, CA9xx = guest, CAAxx = AI agents).
Audience | M365 administrators, security engineers, and MSP technicians deploying or refining Conditional Access in a production tenant. Assumes baseline familiarity with Entra ID, Conditional Access, and KQL.
Licensing | Entra ID P2 (or M365 E5 / A5 / G5) is required for risk-based policies (CA102, CA103, CA604, CA605, CA902) and Token Protection (CA113). Non-P2 tenants can still deploy ~80% of the baseline. Intune is required for device-compliance policies (CA201, CA202, CA204, CA301, CA302, CA606) and App Protection (CA202).
Workbook tabs | (1) Overview — this tab. (2) Deploy Phasing — phased rollout order with prerequisites and risk notes. (3) Groups Required — security groups and named locations to create up front. (4) Account Actions — pre-deploy audit queries (KQL / portal) and tracking template for accounts that need attention before each phase.
Companion files | 'CA Baseline' workbook = the per-policy spec (include / exclude / conditions / access controls / session). 'CA Baseline Summary' workbook = the same data flattened to one-row-per-policy for quick scanning. All three files are designed to live together in the same repo.
Conventions | Every policy is scoped 'Include + Exclude'. Universal exclusions: BG_BreakGlass (2 emergency-access accounts) and CA_ExcludedFromCA (empty escape hatch — populate only during incidents). Service accounts are universally excluded from MFA-bearing policies via CA_ServiceAccount, then have their own scoped policies (CA801–CA804). Naming convention for groups: ca_ prefix for access-control groups, BG_ prefix for break-glass.
How to use | (1) Read the 'Account Actions' tab and run each section's audit queries against the target tenant. Fill the tracking rows with findings. (2) Create the groups in 'Groups Required' and configure the named locations. (3) Enable policies in Phase order from 'Deploy Phasing'. Each phase has prerequisites that MUST be completed first. (4) Every policy goes to Report-only first. Verify zero unintended failures in Sign-in logs before flipping to On. Two policies (CA111, CA603) cannot be Report-only — deploy them last in their phase.
Caveats | (a) The break-glass accounts must exist in the tenant BEFORE deploying any policy. They must be excluded from EVERY policy via the BG_BreakGlass group. (b) Risk-based policies (CA102, CA103, CA604, CA605, CA902) silently no-op without P2 — verify licensing first. (c) CA601 (phish-resistant admin MFA) is the highest-impact policy in the baseline. Botched enforcement = admin lockout. Validate FIDO2 / WHfB / CBA enrollment for EVERY admin role holder before enabling. (d) CA905 (guest non-collab block) needs per-tenant audit — most tenants have at least one legitimate third-party Enterprise app that guests use; that app must be added to CA905 EXCLUDED apps.
Versioning | v2026 baseline. Notable policies vs typical SMB defaults: CA108 (cross-device auth flows), CA111 / CA603 (Continuous Access Evaluation), CA112 (MFA on device register / join), CA113 (token protection), CA601 (phish-resistant admin MFA), CA907 (guest sessions), CAA01 (agent identity, Preview). Adjust per-policy CAxxx codes if you already have a house numbering scheme — the codes are arbitrary, the structure is what matters.
Source / contributions | Maintained by Mirage Informatique. Issues, PRs, and tenant-specific extensions welcome via the repository. This baseline is shared as a reference; adapt to your tenant before deploy. No warranty.

## Deploy Phasing
Mirage CA Baseline v2026 — Phased Deploy Runbook
Phase order is mandatory; each phase has its own prerequisites. Test in Report-only mode before flipping to On. Adapt counts, account names, and geography to the target tenant.
Phase | Policy | Action | Prerequisites (must do first) | Risk if enabled now
PHASE 0 — Pre-deploy prep (no policies enabled, just groundwork)
0 | Create groups | Create | See 'Groups Required' tab — 4 always-required groups + conditionals depending on which policies you deploy. | —
0 | Reclassify service accounts | Move | See 'Account Actions' tab — run the audit query (Service Accounts section) to find tenant service accounts; reclassify into CA_ServiceAccount + CA_ServiceAccount_NonInteractive. | —
0 | Enroll FIDO2 / WHfB / CBA on admins | Enroll | Every account holding a privileged Entra role must have a phish-resistant method registered BEFORE Phase 3 (CA601). See 'Account Actions' for audit queries. | —
0 | Populate named locations | Configure | TRUSTED COUNTRIES + GUEST_TRUSTED_COUNTRIES + (optional) SVC_TRUSTED_IPS + (optional) MALICIOUS IPS. | —
PHASE 1 — Safe to enable (zero failures expected on a clean tenant)
1 | CA101 — Require MFA | Enable | Phase 0 done. | If a baseline 'all users + MFA' policy already exists, this overlaps — disable the legacy one after CA101 confirmed.
1 | CA104 — Block Legacy Auth | Enable | Audit: SigninLogs ¦ where TimeGenerated > ago(30d) ¦ where ClientAppUsed in ('Other clients','POP3','IMAP4','Authenticated SMTP','Exchange ActiveSync'). Confirm zero successful sign-ins before enable. | If legacy auth is in use, mail clients break (Outlook 2010, native mobile mail apps, line-of-business apps using basic auth).
1 | CA105 — Block Unknown Platforms | Enable | Audit: SigninLogs filter on DeviceDetail.operatingSystem not in ('Windows','MacOs','iOS','Android','Linux'). | Rare to break anything in 2026; legacy printers / scanners using EWS may be affected.
1 | CA108 — Block Cross-Device Auth Flows | Enable | Audit: SigninLogs ¦ where AuthenticationProtocol == 'deviceCode' OR has 'authTransfer'. Add legitimate users to CA_DeviceCodeApproved. | Apps relying on device-code flow break (Apple TV / kiosks / Azure CLI in some flows).
1 | CA111 — CAE Standard | Enable | Cannot be Report-only — must be On or Off. | Transparent token revocation; no UX change.
1 | CA112 — MFA on Device Register / Join | Enable | If using Autopilot: AUTOPILOT_DevicePrep group populated with the Autopilot service-account. Otherwise empty. | Discrete user action, low traffic.
1 | CA901 — Guest MFA | Enable | None. | Existing guest MFA policy (if any) overlaps — disable legacy after CA901 confirmed.
1 | CA903 — Guest Block Legacy | Enable | Audit: SigninLogs filter UserType=='Guest' + ClientAppUsed legacy. | Same as CA104 but scoped to guests.
PHASE 2 — Enable after groups + named locations populated
2 | CA102 — User Risk MFA + Pwd Change | Enable | Entra ID P2 confirmed. | Auto-remediation pattern; few prompts on a clean tenant.
2 | CA103 — Sign-In Risk MFA | Enable | Entra ID P2 confirmed. | Few prompts on a clean tenant.
2 | CA106 — Block Outside Trusted Countries | Enable | TRUSTED COUNTRIES populated. CA_TravelException created (empty initially; use PIM-for-Groups for time-bounded exceptions per trip). | Will block users connecting from countries outside the list. Verify against the tenant's actual user-travel patterns.
2 | CA107 — Session Controls | Enable | CA_ServiceAccount populated. | Unmanaged users get 12h re-auth + non-persistent. No impact on managed devices.
2 | CA109 — MFA for Azure Mgmt | Enable | None. | Admins already prompt via CA101 / CA601 path.
2 | CA902 — Guest Sign-In Risk Block | Enable | Entra ID P2 confirmed. | Defense in depth on guests.
2 | CA904 — Guest Country Block | Enable | GUEST_TRUSTED_COUNTRIES populated (typically broader than internal — partner / external collaborator geographies). | Will block guest sign-ins from outside list.
2 | CA907 — Guest Session Controls | Enable | None. | 12h freq + non-persistent for all guests.
2 | CA803 — Service Block Legacy | Enable | CA_ServiceAccount populated. | Defense in depth (CA104 covers globally too).
2 | CA802 — Service Block Outside IPs | Enable | SVC_TRUSTED_IPS populated with all service account source IPs (pull from sign-in logs first — see 'Account Actions'). | Wrong IP list will lock out service accounts.
2 | CA804 — Service Block Non-M365 | Enable | CA_ServiceAccount populated. | Defense in depth — service accounts can only reach Office 365.
2 | CA801 — Service Require MFA (Interactive) | Enable | CA_ServiceAccount_Interactive (likely empty initially). | Only fires for interactive service-account sign-ins.
2 | CA905 — Guest Block Non-Collab Apps | Enable | Audit: find third-party Enterprise apps that legitimate guests use (e.g. partner-provided SharePoint integrations). Add those AppIds to CA905 EXCLUDED apps list — NOT a per-user exclusion. See 'Account Actions'. | Without exclusion: blocks legitimate guest access to third-party Enterprise apps.
PHASE 3 — Enable AFTER admin FIDO2 / WHfB / CBA enrollment confirmed
3 | CA601 — Phish-Resistant Admin MFA | Enable | ALL admins enrolled in FIDO2 / WHfB / CBA. Verify via Entra ID > Authentication methods > Activity > User registration details, OR Get-MgUserAuthenticationMethod. See 'Account Actions'. | WITHOUT ENROLLMENT: admin lockout. Run Report-only first; check sign-in logs for CA601 'reported failure' results before enforcing.
3 | CA602 — Admin Session 4h | Enable | After CA601 stable. | 4h re-auth for admins, non-persistent. Friction but expected.
3 | CA603 — Admin CAE Strict | Enable | After CA601 stable. Cannot be Report-only. | Token revocation on IP changes for admins.
3 | CA604 — Admin User Risk Block | Enable | Entra ID P2 confirmed. | Hard block on High user risk for admins.
3 | CA605 — Admin Sign-In Risk Block | Enable | Entra ID P2 confirmed. | Hard block on High sign-in risk for admins.
PHASE 4 — Enable AFTER Intune fleet validated
4 | CA301 — Compliant Windows | Enable | All corporate Windows is Intune-enrolled with compliance policies. Pilot first with a small group. | Will BLOCK any Windows that is non-compliant or non-hybrid-joined.
4 | CA302 — Compliant macOS | Enable | All corporate Macs Intune-enrolled. | Will BLOCK non-compliant Macs.
4 | CA303 — Limited Browser Unmanaged | Enable | CA301 / CA302 stable. | Browser view-only mode for unmanaged. Fallback path for non-compliant access.
4 | CA606 — Admin Compliant Device | Enable | Admin workstations Intune-managed. | BLOCKS admins on personal / unmanaged devices.
4 | CA202 — Mobile App Protection | Enable | All mobile-heavy users enrolled in Intune App Protection (Outlook Mobile / Teams Mobile / Office Mobile). See 'Account Actions' for the audit query. | WITHOUT PREP: daily mobile users blocked on every sign-in. Audit sign-in logs for AADSTS530002 / 'app protection' failure codes; do not enable until that list is empty or all affected users are enrolled.
4 | CA201 — Intune Enrolling MFA | Enable | None — only fires during enrollment. | No daily impact.
PHASE 5 — Optional / per-tenant context
5 | CA110 — Block Malicious IPs | Optional | Maintained threat-feed integration (named location populated with bad IPs). | Skip unless org has a maintained feed.
5 | CA113 — Token Protection (Pilot) | Optional | Create CA_TokenProtection_Pilot with 2-3 IT users. | Pilot scope only. Windows-only, EXO / SPO / Teams native apps.
5 | CA114 — Internal Terms of Use | Optional | Per-tenant ToU agreement object GUID. | Skip unless regulatory.
5 | CA906 — Guest Terms of Use | Optional | Per-tenant guest ToU GUID. | Skip unless regulatory.
5 | CA204 — Compliant Mobile (MDM) | Recommended | Skip if tenant is APP-only on mobile (most SMBs). | Deploy if tenant wants to fully enroll personal cellphones in MDM.
5 | CA701 / CA702 — App-specific MFA | Per-tenant | CA701 (FortiClient) and CA702 (Salesforce) are template examples. Replace with the actual SaaS / SSO apps in the target tenant. Add additional CA70X policies — one per app — as needed. | Skip if app not present.
5 | CAA01 — Agent Block High Risk | Wait | Microsoft agent identity GA in tenant (Preview as of v2026 publication). | Pilot when GA — populate CA_ExcludedAgents (empty escape hatch).

## Groups Required
Mirage CA Baseline v2026 — Required Groups & Named Locations
Minimum set for the baseline. Conditional groups are only needed if you deploy the related policy.
Group / Location | Type | Required? | Initial members at deploy | Used by which policies
REQUIRED — baseline will not function without these
BG_BreakGlass | Security group | YES | The 2 break-glass / emergency access accounts (should already exist in tenant; create if not). | All policies (universal escape)
CA_ExcludedFromCA | Security group | YES | Empty at deploy. Populate ONLY during incident response. | All policies (universal escape)
CA_ServiceAccount | Security group | YES | Tenant-specific service accounts (reporting, automation, MSP-tooling). Identify via the audit query in 'Account Actions' > Service Accounts section. | CA101–CA799 (excluded), CA802 / CA803 / CA804 (included)
CA_ServiceAccount_NonInteractive | Security group | YES | Same accounts that authenticate via cert / secret / managed identity (no interactive sign-in path). | CA801 (excluded — they cannot do MFA)
CONDITIONAL — create only if deploying the related policy
AUTOPILOT_DevicePrep | Security group | If Autopilot used | Empty if no Autopilot in use. Otherwise the Autopilot service-account. | CA112, CA201 (excluded during enrollment)
CA_ServiceAccount_Interactive | Security group | If interactive svc accts | Empty initially. Add any service accounts that DO sign in interactively (e.g. break-glass-style auth). | CA801 (included)
CA_TravelException | Security group | If supporting travel | Empty. Use PIM-for-Groups or access reviews for time-bound assignments per trip. | CA106 (excluded for time-bound exception)
CA_TokenProtection_Pilot | Security group | If running CA113 pilot | 2-3 IT users for the Token Protection pilot. | CA113 (included — pilot only)
CA_DeviceCodeApproved | Security group | If any app needs device code | Empty. Add only if a specific app legitimately requires device-code flow. | CA108 (excluded)
CA_VPN_Users | Security group | If deploying CA701 | Empty. Add the user population that should be MFA-gated for VPN sign-on (template example). | CA701 (included)
CA_ExcludedAgents | Security group | When CAA01 enabled | Empty. Escape hatch for agent troubleshooting / incident. | CAA01 (excluded)
NAMED LOCATIONS — configure these too
TRUSTED COUNTRIES | Country location | YES | Tenant home country + key business geographies (typical SMB: 1-3 countries). Adjust per internal travel patterns. | CA106
GUEST_TRUSTED_COUNTRIES | Country location | YES | Typically broader than internal — geographies of external collaborators (partners, clients, vendors). Adjust per tenant. | CA904
SVC_TRUSTED_IPS | IP range location | YES | Source IPs for all service accounts. Pull from sign-in logs (see 'Account Actions' > Service Accounts audit query — capture the IPs column). | CA802
MALICIOUS IPS | IP range location | Optional | Skip unless threat-feed integration is in place. | CA110
DROPPED — groups from earlier drafts that are NOT needed (kept for reference)
CA_MSP_PartnerUsers | — | NOT NEEDED | Native CA exclusion 'Service provider users' toggle handles MSP guest scope. No custom group required. | Replaced by built-in External user type
ADM_AllAdmins | — | NOT NEEDED | Native CA 'Directory roles (selected)' handles admin scope. No custom group needed. | Replaced by built-in directory role selector
USR_AllInternals | — | NOT NEEDED | Inc=All users + per-policy excludes (CA_ServiceAccount, All Guest/External, etc.) achieves the same scope without a synced group. | Replaced by Inc=All users + excludes pattern

## Account Actions
Mirage CA Baseline v2026 — Pre-deploy Audit & Account Tracker
Run the audit queries below against the target tenant. Fill the TEMPLATE rows with findings. Complete each section before the corresponding phase in 'Deploy Phasing'.
Item | Category | Action | What to do / Decision rule / Account UPN | Why / Notes
MASTER AUDIT — run after each policy goes Report-only (and re-run before flipping to On)
Master Audit | KQL | Run query | SigninLogs ¦ where TimeGenerated > ago(7d) ¦ where ConditionalAccessPolicies != "[]" ¦ mv-expand ConditionalAccessPolicies ¦ extend PolicyName = tostring(ConditionalAccessPolicies.displayName), Result = tostring(ConditionalAccessPolicies.result) ¦ where Result in ("failure", "reportOnlyFailure", "interrupted", "reportOnlyInterrupted") ¦ summarize Failures = countif(Result in ("failure", "reportOnlyFailure")), UserActionRequired = countif(Result in ("interrupted", "reportOnlyInterrupted")), Apps = make_set(AppDisplayName, 5), LastSeen = max(TimeGenerated) by UserPrincipalName, PolicyName ¦ order by UserPrincipalName asc, Failures desc, UserActionRequired desc | Surfaces every user × CA policy interaction where the policy failed or required user action, across both On and Report-only states. The 'reportOnlyFailure' / 'reportOnlyInterrupted' results are pre-enforcement signal — they are what WILL block users when you flip the policy to On. Workspace: any tenant with sign-in logs forwarded to Log Analytics / Sentinel. Without a Log Analytics workspace: substitute Entra ID > Sign-in logs > Conditional Access tab in the portal (filter by policy name).
Decision A | Rule | Interpret results | Failures = HARD blocks (the policy denied access). UserActionRequired = the user was prompted (MFA / ToU / etc.) and either complied or abandoned. The 'reportOnly*' variants mean the policy is in audit mode — same outcomes WILL apply once enforced. Acceptable Failures: explicit blocks of legacy auth / unknown platforms / risky sign-ins. Unacceptable Failures: legitimate users on legitimate apps. Acceptable UserActionRequired: MFA prompts. Unacceptable: prompts the user cannot satisfy (e.g. CA601 prompting an admin without FIDO2/WHfB/CBA enrolled). | Pattern matters more than count. One user × one policy with 50+ failures = investigate. Many users × one policy with low counts = expected (e.g. CA101 prompting MFA).
Decision B | Rule | Drill-down filters | To investigate one policy: append `¦ where PolicyName contains "CA601"` (or the policy name). To investigate one persona: append `¦ where UserPrincipalName in (...)` or join against a group membership query. To investigate guests only: add `¦ extend UserType = tostring(UserType_string) ¦ where UserType == "Guest"` upstream of the summarize. To investigate apps for CA905 exclusion: replace summarize with `by UserPrincipalName, AppDisplayName, AppId` to capture AppId. | Each persona section below references this query with the appropriate filter.
TEMPLATE — log findings (one row per user × policy that needs action)
<UPN> | <Policy> | <# Failures / # Interrupted> | <action: enroll / exclude / move group / accept> | <root cause, apps, last seen>
<UPN> | <Policy> | <# Failures / # Interrupted> | <action: enroll / exclude / move group / accept> | <root cause, apps, last seen>
<UPN> | <Policy> | <# Failures / # Interrupted> | <action: enroll / exclude / move group / accept> | <root cause, apps, last seen>
<UPN> | <Policy> | <# Failures / # Interrupted> | <action: enroll / exclude / move group / accept> | <root cause, apps, last seen>
SERVICE ACCOUNTS — reclassify before Phase 1 (CA101) and Phase 3 (CA601)
Audit (1/2) | KQL | Run query | SigninLogs ¦ where TimeGenerated > ago(7d) ¦ where AppDisplayName has_any ("PowerShell","Microsoft Graph","Azure CLI","Exchange Online") ¦ where ResultType == 0 ¦ summarize cnt=count(), apps=make_set(AppDisplayName), ips=make_set(IPAddress) by UserPrincipalName ¦ where cnt > 50 ¦ sort by cnt desc | Find UPN-based accounts running automation. Capture the IPs column for SVC_TRUSTED_IPS.
Audit (2/2) | Portal | Cross-check roles | Entra ID > Roles & administrators > each privileged role > Members. PowerShell: Get-MgRoleManagementDirectoryRoleAssignment -All ¦ Where-Object PrincipalType -eq 'User' | Identify which audit-flagged accounts hold admin roles (cannot satisfy CA601 phish-resistant MFA).
Decision A | Rule | Reclassify (non-int) | Pure non-interactive (cert / secret) → CA_ServiceAccount + CA_ServiceAccount_NonInteractive. Remove any admin role assignment. | Excluded from CA101 + CA601. Cannot do interactive MFA.
Decision B | Rule | Reclassify (mixed) | Mixed interactive + non-interactive → CA_ServiceAccount + CA_ServiceAccount_Interactive. | CA801 will require MFA only on interactive sign-ins.
Decision C | Rule | Migrate to SP | Has admin role + cannot remove → migrate to managed identity OR app registration with cert auth. | Best practice. Eliminates secret rotation; native to Entra.
TEMPLATE — fill with tenant findings (add rows as needed)
<UPN> | <type> | <action> | <group / decision> | <sign-in count, IPs, role, etc.>
<UPN> | <type> | <action> | <group / decision> | <sign-in count, IPs, role, etc.>
<UPN> | <type> | <action> | <group / decision> | <sign-in count, IPs, role, etc.>
<UPN> | <type> | <action> | <group / decision> | <sign-in count, IPs, role, etc.>
ADMINS — enroll FIDO2 / WHfB / CBA before Phase 3 (CA601)
Audit (1/2) | Portal/PS | List admins | Entra ID > Roles & administrators > expand each privileged role. PowerShell: Get-MgRoleManagementDirectoryRoleAssignment -All -ExpandProperty * ¦ Where-Object {$_.RoleDefinition.IsPrivileged -eq $true} | List ALL accounts holding any privileged Entra role.
Audit (2/2) | Portal | Check methods | Entra ID > Authentication methods > Activity > User registration details. Filter: Method registered = passkey (FIDO2) / Windows Hello / certificate-based. | Confirm a phish-resistant method is enrolled per admin BEFORE enabling CA601.
Decision | Rule | Enroll one of | FIDO2 security key ¦ Windows Hello for Business ¦ Certificate-Based Auth. | Choose per admin device profile. Required to pass CA601; otherwise lockout.
Verify | KQL filter | Post-Report-only check | After CA601 is in Report-only, filter master audit: ¦ where PolicyName contains "CA601". Any 'reportOnlyFailure' result on an admin = that admin will be locked out when you flip CA601 to On. Resolve before enforcement. | Use the MASTER AUDIT (top of tab) with this filter.
TEMPLATE — fill with tenant findings (add rows as needed)
<admin UPN> | Admin | Enroll | <FIDO2 ¦ WHfB ¦ CBA> | <current methods, sign-in volume, role>
<admin UPN> | Admin | Enroll | <FIDO2 ¦ WHfB ¦ CBA> | <current methods, sign-in volume, role>
<admin UPN> | Admin | Enroll | <FIDO2 ¦ WHfB ¦ CBA> | <current methods, sign-in volume, role>
<admin UPN> | Admin | Enroll | <FIDO2 ¦ WHfB ¦ CBA> | <current methods, sign-in volume, role>
MOBILE-HEAVY USERS — enroll Intune APP before Phase 4 (CA202)
Audit | KQL | Find APP-blocked | SigninLogs ¦ where TimeGenerated > ago(30d) ¦ where DeviceDetail.operatingSystem in ("iOS","Android") ¦ where AppDisplayName has_any ("Outlook","Teams","Office") ¦ where ResultType != 0 and ConditionalAccessStatus != "success" ¦ summarize cnt=count(), apps=make_set(AppDisplayName) by UserPrincipalName ¦ sort by cnt desc | Surface users who would be blocked by CA202 (mobile App Protection).
Decision | Rule | Enroll APP | Per affected user: enroll Outlook Mobile + Teams Mobile + Office Mobile in Intune App Protection via Company Portal (or auto-enroll via Intune APP policy + targeted assignment). | Required to pass CA202.
Verify | KQL filter | Post-Report-only check | After CA202 is in Report-only, filter master audit: ¦ where PolicyName contains "CA202". Any 'reportOnlyFailure' = that user lacks Intune App Protection on a mobile app and will be blocked at enforcement. | Use the MASTER AUDIT (top of tab) with this filter.
TEMPLATE — fill with tenant findings (add rows as needed)
<UPN> | Internal | Enroll APP | <Outlook / Teams / Office> | <failure count, primary platform>
<UPN> | Internal | Enroll APP | <Outlook / Teams / Office> | <failure count, primary platform>
<UPN> | Internal | Enroll APP | <Outlook / Teams / Office> | <failure count, primary platform>
<UPN> | Internal | Enroll APP | <Outlook / Teams / Office> | <failure count, primary platform>
GUESTS WITH 3RD-PARTY APP DEPENDENCIES — CA905 exclusion before Phase 2
Audit | KQL | Find guest blocks | SigninLogs ¦ where TimeGenerated > ago(30d) ¦ where UserType == "Guest" ¦ where ConditionalAccessStatus == "failure" ¦ summarize cnt=count() by UserPrincipalName, AppDisplayName, AppId ¦ sort by cnt desc | Surface guests blocked on non-Office365 Enterprise apps. Identify legitimate partner integrations.
Decision | Rule | Add app exclusion | Per legitimate 3rd-party Enterprise app: add the AppId to CA905 EXCLUDED apps list — NOT a per-user exclusion. | Allows guest access to legitimate partner integrations while keeping CA905 broad. The exclusion is per-app (Enterprise application object), so it covers all guests using that app.
Verify | KQL filter | Post-Report-only check | After CA905 is in Report-only, filter master audit: ¦ where PolicyName contains "CA905" + change `summarize ... by UserPrincipalName, AppDisplayName, AppId`. Any 'reportOnlyFailure' on a legitimate guest = that AppId needs to be added to CA905 EXCLUDED apps. | Use the MASTER AUDIT (top of tab) with this filter.
TEMPLATE — fill with tenant findings (add rows as needed)
<Enterprise app + AppId> | App excl. | Add to CA905 exclusion | <description of legitimate use> | <block count, affected guests>
<Enterprise app + AppId> | App excl. | Add to CA905 exclusion | <description of legitimate use> | <block count, affected guests>
<Enterprise app + AppId> | App excl. | Add to CA905 exclusion | <description of legitimate use> | <block count, affected guests>
<Enterprise app + AppId> | App excl. | Add to CA905 exclusion | <description of legitimate use> | <block count, affected guests>
BREAK-GLASS — validate BEFORE any policy enable
Verify (1/3) | Portal | Confirm 2 BG accounts | Entra ID > Users — confirm 2 dedicated cloud-only accounts exist (e.g. break-glass-01, break-glass-02). Excluded from sync, password rotated and stored in physical safe. | Industry standard: 2 accounts so one can be available even if the other is compromised / lost.
Verify (2/3) | Portal | Confirm BG_BreakGlass membership | Both break-glass UPNs are members of BG_BreakGlass group AND assigned Global Administrator role (eligible via PIM acceptable, but standing assignment is safer for emergency). | Group is excluded from EVERY policy in this baseline. Standing GA = guaranteed sign-in path.
Verify (3/3) | Process | Test sign-in | Manually sign in with one BG account. Verify it bypasses all CA policies (Sign-in logs > Conditional Access tab should show 'Not applied' for every policy). | Do this BEFORE enabling Phase 1. Re-test after each phase rollout.